### Minutes of Meeting (Technical/Contract)

MoM — Technical & Contract Review Meeting
Subject: Progress & Issues – 220 kV DC Transmission Line from Maheshwaram to Kandukur
Date: 28-10-2025
Time: 11:00 hrs – 13:00 hrs
Venue: Conference Hall, CE (Construction), Vidyut Soudha, Hyderabad

Attendees:

- CE (Construction) – Chair

- SE (Construction) / Hyderabad Circle

- EE/Construction – Maheshwaram Division

- EE/MRT – Hyderabad

- Representative – Finance (Works)

- Representative – M/s XYZ Infra Projects (EPC Contractor)

- AEs/ADENs concerned (list as per attendance sheet)

### Decisions Taken (D)

D1. Foundation & Erection Milestones

- Approved revised milestone plan:

  - All foundations up to Loc. 85 to be completed by 30-11-2025.

  - Tower erection up to Loc. 70 to be completed by 20-12-2025.

D2. Stub/Template Deviations

- Any deviation from approved tower schedule/drawings shall not be adopted at site without written approval from EE/Const → SE/Const.

- Contractor’s earlier request for alternate stub at Loc. 43 kept rejected, to be rectified as per original design.

D3. Insulator & Conductor Supply

- CE (Const) concurred for single consolidated supply schedule for remaining insulators & Panther conductor; no piecemeal indents.

- XYZ Infra to adhere to approved makes and IS/IEC specs; any change requires prior written approval.

D4. Right of Way (RoW) Issues

- For RoW at Loc. 62–65 (private lands), decision taken to route matter through District Administration with support from contractor. No change in alignment at this stage.

### 2) Action Items (AI)

AI 1:

- Task: Submit detailed catch-up schedule (location-wise foundations/erection/stringing).

- Owner: M/s XYZ Infra (Project Manager).

- Due Date: 02-11-2025.

AI 2:

- Task: Issue written clarification on design & stub details at Loc. 40–45 and circulate to site engineers.

- Owner: EE/Const (Design), Hyderabad.

- Due Date: 31-10-2025.

AI 3:

- Task: Arrange joint inspection for RoW-affected locations with Revenue officials; prepare minutes and photographs.

- Owner: SE/Const, with XYZ Infra.

- Due Date: 10-11-2025.

AI 4:

- Task: MRT to inspect and certify received tension and suspension insulators (sampling) and issue QC note.

- Owner: EE/MRT, Hyderabad.

- Due Date: 05-11-2025.

AI 5:

- Task: Finance (Works) to clear all undisputed RA bills within 10 days of complete documentation to avoid cash-flow delays.

- Owner: AO/Works.

- Due Date: Ongoing; to review in next meeting.

### 3) Risks / Dependencies

- RoW Clearance: Delay beyond 30-11-2025 at Loc. 62–65 may affect stringing schedule; SE/Const to escalate to CE (Const) if no progress by 15-11-2025.

- Monsoon Impact: Early rains may hamper excavation & concreting; contractor to plan resources accordingly.

- Quality Compliance: Any work found deviating from drawings/specs will be rejected at contractor’s risk & cost; payment will be linked to QC clearance.

### 4) Next Meeting

- Date: 18-11-2025 at 11:00 hrs

- Venue: CE (Construction) Chamber / VC

- Agenda: Review progress against revised milestones; RoW status; QC observations; decision on any pending deviations.

Chief Engineer (Construction)
APTRANSCO, Vidyut Soudha, Hyderabad